SUPERTEAM VIETNAM · COLOSSEUM BUILDER PROGRAM

Onchain Time
Builder Sprint

Program Funding & Delivery Proposal

Learn online. Build together. Iterate toward Colosseum.

| PREPARED FOR Superteam Vietnam | PROGRAM OPENS 4 September 2026 |
| --- | --- |
| IN-PERSON 18–20 September 2026 | LOCATION Da Nang, Vietnam |
| PARTICIPANTS 70 builders · 11–12 teams | FORMAT Friday night + 1.5 days |
| FUNDING REQUEST VND 60 million | OPERATIONS LEAD Danh |

DECISION REQUESTED Approve a VND 60 million program envelope for catering and operations, with the venue sourced separately as an in-kind partnership.

Prepared by Hieu and the organizing team · 31 August 2026

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

01 / FUNDING CASE

# A compact activation program for the Colosseum pipeline

The Onchain Time Builder Sprint gives Vietnam-based builders two weeks of structured online preparation and a focused Da Nang build weekend. It is designed as part of Superteam Vietnam's Colosseum subtrack effort: teams leave with real products, public iteration evidence and a clear continuation path.

FUNDING PURPOSE The requested VND 60 million pays for participant catering and accountable event operations. It does not fund a local prize pool, venue rent or website-development labor.

## What Superteam Vietnam is funding

| Funding objective | Delivery commitment |
| --- | --- |
| Builder access | Keep the in-person program free for selected participants and provide essential meals and hydration. |
| Operational reliability | Fund named delivery ownership, event crew, connectivity backup, safety supplies, signage and documentation. |
| Subtrack readiness | Move 11–12 teams from early concepts to submitted working checkpoints and clear next-step plans. |
| Ecosystem visibility | Publish projects, participation evidence, approved media and a post-event outcome report. |

## Expected headline outcomes

- Approximately 70 participating builders organized into 11–12 teams.

- 11–12 direct website submissions completed before Sunday demos.

- At least 80% of teams publishing two or more meaningful iteration checkpoints.

- At least eight teams continuing toward the Superteam Vietnam Colosseum subtrack.

- A documented and repeatable online-to-offline builder-program model for future cohorts.

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

02 / PROGRAM DESIGN

# Online learning first; in-person time for execution

The program website is the learning and iteration layer, not merely a registration page. Materials open two weeks before the event, and all projects, checkpoints, feedback and final submissions are recorded directly online.

## Program model

| Component | Plan |
| --- | --- |
| Online preparation | All learning material and build guidance available from 4 September; teams form, define users and begin project pages online. |
| In-person acceleration | Friday kickoff, a focused Saturday build day and a Sunday morning demo-and-feedback session. |
| Website workflow | Learning, team workspaces, checkpoints, feedback and final submission all live on the program website. |
| Output | 11–12 working project submissions, each with a defined user, functioning product journey and continuation plan. |
| Incentive model | No local prize. Teams build toward the Superteam Vietnam Colosseum subtrack, with a stated total prize pool of US$10,000. |

## Why this format

- Preparation happens before the room. The website carries the learning load, so venue time is used for building, testing and mentor feedback.

- The weekend is deliberately compact. Saturday ends at 17:00 without dinner; Sunday closes at 11:30 without lunch.

- Iteration leads to continuation. Teams are recognized for progress—not ranked locally—and their project histories remain online through the Colosseum cycle.

## Website journey

- Learn. Review the prompt, Solana resources, rules and build guidance.

- Form. Create a team, choose a user niche and publish the problem.

- Build. Maintain links, milestones, evidence and an iteration log.

- Submit. Finalize the same project page directly on the website.

- Continue. Use its history and feedback to prepare the subtrack entry.

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

03 / IN-PERSON DELIVERY

# One evening, one full day and one focused morning

The schedule protects deep building time while controlling food and operating costs. There is no Saturday dinner, no overnight program and no Sunday lunch.

## Friday, 18 September · kickoff

| Time | Activity | Result |
| --- | --- | --- |
| 17:30 | Registration and light dinner | Teams checked in and settled |
| 18:15 | Welcome, program purpose and partner acknowledgement | Shared expectations |
| 18:35 | Build prompt, safeguards and website workflow | Submission requirements understood |
| 19:00 | Team plan review and mentor office hours | Saturday priorities locked |
| 20:30 | Checkpoint published on website | Visible starting point |
| 21:00 | Participant close | No overnight program |

## Saturday, 19 September · build and iterate

| Time | Activity | Result |
| --- | --- | --- |
| 09:00 | Stand-up and technical readiness | Blockers surfaced |
| 09:20 | Focused build block | Core journey implemented |
| 11:45 | Checkpoint review | Evidence and next changes recorded |
| 12:00 | Lunch | On-site meal |
| 13:00 | Build, user testing and mentor rotations | Product iteration |
| 15:15 | Tea break | Short reset |
| 15:35 | Final Saturday build block | Demo path stabilized |
| 16:35 | Website checkpoint and Sunday briefing | Submission plan confirmed |
| 17:00 | Close | No Saturday dinner |

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

04 / DEMO AND SUBMISSION

# Twelve teams can demo within two hours

Sunday is a feedback checkpoint, not a local awards ceremony. Two parallel tracks provide enough capacity for every expected team while allowing the event to close at 11:30.

## Sunday, 20 September · 08:30–11:30

| Time | Activity | Output |
| --- | --- | --- |
| 08:30 | Coffee, light breakfast and final fixes | Demo-ready project |
| 09:15 | Direct website submission deadline | Stable project page and QR code |
| 09:20 | Demo briefing and track assignment | Teams and audiences positioned |
| 09:25–10:55 | Six rounds across two parallel demo tracks | Capacity for 12 complete demos |
| 10:55 | Feedback capture and transition | Next changes recorded online |
| 11:05 | Subtrack continuation plan | Owners, dates and pathway confirmed |
| 11:20 | Partner acknowledgement, photo and close | Program closes before lunch |
| 11:30 | Participants depart | No Sunday lunch |

DEMO CAPACITY 2 tracks × 6 rounds = 12 team demos. Each 15-minute slot allows approximately 7 minutes for the product, 5 minutes for feedback and 3 minutes for transition.

- Two separated zones. Each track needs a display, power, clear sound and one anchor mentor or facilitator.

- Website-first evidence. Every demo begins from the submitted project page and QR code.

- No local ranking. The close recognizes progress and readiness; the external subtrack governs its own eligibility and prizes.

## Feedback lenses

| Lens | Question |
| --- | --- |
| User clarity | Is the target user specific and credible? |
| Value | Does the time-based exchange solve a real problem? |
| Product | Can a user complete the essential journey? |
| Evidence | What did the team learn from real feedback or behavior? |
| Iteration | What changed across checkpoints, and why? |
| Continuation | What is the team's next test during Colosseum? |

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

05 / DELIVERY OWNERSHIP

# Clear accountability across program and operations

Danh serves as operations lead, with authority over readiness, suppliers, crew and live-event escalation. Hieu owns program direction, ecosystem coordination and the funding relationship.

| Role | Accountability |
| --- | --- |
| Hieu · program lead | Program design, Superteam Vietnam coordination, venue relationship, learning direction and final outcome report. |
| Danh · operations lead | Master run of show, procurement, crew roster, venue readiness, participant service and incident escalation. |
| Mentors · to be confirmed | Product, technical and go-to-market feedback online and during the build weekend. |
| Four-person event crew | Registration, room operations, catering, timekeeping, technical support and documentation. |
| Venue partner | In-kind space, utilities, agreed furniture/AV, security, cleaning and venue technical contact. |
| Community collaborators | Local outreach and community support, subject to confirmation. |

## Operating checkpoints

- By 4 September. Confirm funding, venue direction, website readiness and public program message.

- By 11 September. Confirm suppliers, crew, mentors, registration status and draft room plan.

- By 17 September. Complete readiness gate for teams, dietary/accessibility lists, venue test and demo-track plan.

- Each event day. Run internet, power, AV, safety, QR-code and supplier checks before doors open.

- By 27 September. Deliver the outcome report, financial reconciliation and project continuation status.

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

06 / FUNDING REQUEST

# VND 60 million for catering and operations

The cash plan is built for 80 catered people: approximately 70 builders plus mentors, crew and partners. Venue rental is excluded because the venue will be requested as an in-kind contribution.

## Catering · VND 25.6 million

| Item | Planning basis | Budget |
| --- | --- | --- |
| Friday light dinner | 80 × VND 80,000 | VND 6.4m |
| Saturday lunch | 80 × VND 80,000 | VND 6.4m |
| Saturday tea break | 80 × VND 55,000 | VND 4.4m |
| Sunday coffee + light breakfast | 80 × VND 55,000 | VND 4.4m |
| Water and continuous coffee | Weekend provision | VND 2.4m |
| Delivery and dietary buffer | Approximately 5% | VND 1.6m |
| Catering subtotal |  | VND 25.6m |

## Operations · VND 28.0 million

| Item | Scope | Budget |
| --- | --- | --- |
| Operations lead | Planning and delivery leadership | VND 8.0m |
| Event crew | Four-person support across 2.5 days | VND 4.5m |
| AV, internet and power backup | Only for gaps in venue provision | VND 3.0m |
| Photography and media | Selected event coverage | VND 4.0m |
| Printing and signage | Badges, schedules and partner visibility | VND 2.5m |
| Supplies, first aid and cleaning buffer | Consumables and safety | VND 2.5m |
| Mentor and local transport | Reasonable reimbursements | VND 2.0m |
| Website operating services | Hosting, email and storage; not development | VND 1.5m |
| Operations subtotal |  | VND 28.0m |

## Funding summary

| Category | Amount | Share |
| --- | --- | --- |
| Catering | VND 25.6m | 42.7% |
| Operations | VND 28.0m | 46.7% |
| Contingency and procurement variation | VND 6.4m | 10.6% |
| Total funding requested | VND 60.0m | 100% |

EXCLUSIONS No local prize pool · no venue rent · no website-development labor · mentors unpaid except reasonable transport · the US$10,000 subtrack prize pool is external to this event budget.

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

07 / FINANCIAL CONTROLS

# A simple, accountable use-of-funds process

The funding envelope should move fast enough to secure suppliers while remaining easy to reconcile. The following controls are proposed for agreement with Superteam Vietnam.

## Recommended funding process

- Approve the envelope. Confirm the VND 60 million cap and eligible categories before supplier commitments.

- Release funds before supplier deadlines. A single pre-event transfer is operationally simplest; any tranche arrangement should still cover deposits and procurement by 7 September.

- Record commitments. Danh maintains the purchase log, supplier quotation/confirmation, owner, due date and payment status.

- Control material changes. Movement above 10% between major categories requires written approval from the program lead and funder contact.

- Reconcile and report. Receipts, invoices, actual-versus-plan variance and unused funds are reported within seven days after the event.

## Approval matrix

| Decision | Owner | Evidence |
| --- | --- | --- |
| Supplier selection and logistics | Danh | Quotation or written price confirmation |
| Program-scope and participant decisions | Hieu | Program plan and participant records |
| Material category variance | Hieu + funder contact | Written approval |
| Payment and expense record | Danh | Invoice, receipt or approved exception note |
| Final reconciliation | Hieu | Actual-versus-budget statement and report |

## Contingency use

- Attendance or dietary changes that affect catering quantities.

- Internet, display or power backup not included by the final venue.

- Last-mile transport, safety or operational requirements discovered during the site check.

- Unavoidable supplier variation; contingency is not a discretionary prize or marketing pool.

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

08 / MEASUREMENT

# Report outcomes that reflect building and continuation

Attendance matters, but the primary evidence is what teams create, how they iterate and whether they continue into the subtrack effort. A concise program and financial report will be delivered within seven days.

| Measure | Target | Evidence |
| --- | --- | --- |
| Builder participation | 70 participants | Registration and check-in |
| Active teams | 11–12 teams | Website team workspaces |
| Sunday submissions | 11–12 projects | Timestamped website submissions |
| Meaningful iteration | 80% publish 2+ checkpoints | Project histories |
| Subtrack continuation | At least 8 teams | Post-event project updates |
| Delivery quality | Program closes on schedule with no major incident | Run-of-show and incident log |
| Financial accountability | 100% of material spend reconciled | Receipts and variance report |

## Post-event report contents

- Attendance, team, submission and checkpoint totals.

- Project directory with links and concise descriptions.

- Continuation status and next milestones for each team.

- Approved media and partner-recognition record.

- Actual-versus-budget statement with material variance explanations.

- Operational lessons and recommendations for a future cohort.

ONCHAIN TIME BUILDER SPRINT  /  SUPERTEAM VIETNAM FUNDING PROPOSAL

09 / RISKS AND DECISION

# The delivery risks are known and manageable

The main risks are preparation, infrastructure, attendance and cost variance. Each has a specific owner and mitigation path.

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Teams arrive unprepared | Online readiness gate by 17 September; targeted remote support before Friday | Program |
| Venue not confirmed | Parallel venue outreach, site checklist and decision deadline | Hieu |
| Internet instability | Load test, venue technical contact and budgeted backup | Ops + venue |
| Lower Sunday attendance | Slots confirmed Saturday; submission deadline tied to demo; close before lunch | Danh |
| Demo tracks interfere | Two rooms or acoustically separated zones with independent displays | Venue |
| Catering variance | Headcount lock, dietary list and controlled buffer | Danh |
| No local prize reduces urgency | Public checkpoints, mentor access and clear subtrack continuation value | Program |

## Requested decisions

- Confirm program alignment. Approve the event as part of the Superteam Vietnam Colosseum subtrack effort and confirm the public wording.

- Approve VND 60 million. Authorize the catering and operations envelope and the agreed transfer process.

- Confirm reporting contact. Name the person who approves material variances and receives the final report.

- Confirm subtrack pathway. Validate eligibility, prize-language and direct next steps for participating projects.

- Release program launch. Allow materials and registration communication to go live from 4 September 2026.

TIMING Funding and program wording should be confirmed as soon as possible, ideally by 4 September, so suppliers and participant communication can proceed without compression.

## Reference note

Colosseum's published 2026 schedule lists the fall online hackathon as 28 September–2 November 2026: Colosseum Codex — 2026 Hackathons

Superteam Vietnam subtrack eligibility, branding and prize terms remain governed by the applicable program rules and final ecosystem coordination.