SUPERTEAM VIETNAM · COLOSSEUM BUILDER PROGRAM

Onchain Time
Builder Sprint

Venue In-Kind Partnership Proposal

Learn online. Build together. Iterate toward Colosseum.

| PREPARED FOR Prospective Venue Partner | PROGRAM OPENS 4 September 2026 |
| --- | --- |
| IN-PERSON 18–20 September 2026 | LOCATION Da Nang, Vietnam |
| PARTICIPANTS 70 builders · 11–12 teams | FORMAT Friday night + 1.5 days |
| VENUE REQUEST Space and facilities in kind | CASH REQUEST None |

PARTNERSHIP REQUEST Provide a safe, accessible and builder-ready venue at no charge for Friday evening, Saturday daytime and Sunday morning. Superteam Vietnam funds the program's catering and operations; no cash sponsorship is requested from the venue partner.

Prepared by Hieu and the organizing team · 31 August 2026

ONCHAIN TIME BUILDER SPRINT  /  VENUE IN-KIND PROPOSAL

01 / THE OPPORTUNITY

# Become the physical home of a focused builder program

The Onchain Time Builder Sprint is a two-week online learning and product-iteration program culminating in a compact in-person weekend in Da Nang. It is part of Superteam Vietnam's Colosseum subtrack effort and is designed for building, feedback and continuation—not a local prize ceremony.

DECISION REQUESTED Confirm an in-kind venue partnership for up to 80 people, with access from 18–20 September 2026 and the facilities described in this proposal.

## Program model

| Component | Plan |
| --- | --- |
| Online preparation | All learning material and build guidance available from 4 September; teams form, define users and begin project pages online. |
| In-person acceleration | Friday kickoff, a focused Saturday build day and a Sunday morning demo-and-feedback session. |
| Website workflow | Learning, team workspaces, checkpoints, feedback and final submission all live on the program website. |
| Output | 11–12 working project submissions, each with a defined user, functioning product journey and continuation plan. |
| Incentive model | No local prize. Teams build toward the Superteam Vietnam Colosseum subtrack, with a stated total prize pool of US$10,000. |

## Why this format

- Preparation happens before the room. The website carries the learning load, so venue time is used for building, testing and mentor feedback.

- The weekend is deliberately compact. Saturday ends at 17:00 without dinner; Sunday closes at 11:30 without lunch.

- Iteration leads to continuation. Teams are recognized for progress—not ranked locally—and their project histories remain online through the Colosseum cycle.

## What the venue is—and is not—being asked to provide

| Requested from venue | Covered by organizers / Superteam Vietnam |
| --- | --- |
| Space, utilities, agreed furniture and included AV | Catering, event staffing and participant operations |
| Weekend access, security, cleaning and venue contact | Mentors, registration, website and project submission workflow |
| Internet and power suitable for the agreed capacity | Event supplies, documentation and approved photography |
| Two separated Sunday demo zones | Program content, timekeeping, feedback and post-event reporting |

ONCHAIN TIME BUILDER SPRINT  /  VENUE IN-KIND PROPOSAL

02 / ACCESS AND SCHEDULE

# A bounded request across three calendar days

The program uses Friday evening for kickoff, Saturday for concentrated building and Sunday morning for direct website submission and two parallel demo tracks. There are no overnight activities.

## Requested venue access

| Day | Requested access | Participant program | Purpose |
| --- | --- | --- | --- |
| Fri, 18 Sep | 16:30–21:30 | 17:30–21:00 | Setup, registration, kickoff and pack-down |
| Sat, 19 Sep | 08:00–17:30 | 09:00–17:00 | Setup, full build day and close; no dinner |
| Sun, 20 Sep | 08:00–12:00 | 08:30–11:30 | Breakfast, submissions, demos and close; no lunch |

## Friday, 18 September · kickoff

| Time | Activity | Result |
| --- | --- | --- |
| 17:30 | Registration and light dinner | Teams checked in and settled |
| 18:15 | Welcome, program purpose and partner acknowledgement | Shared expectations |
| 18:35 | Build prompt, safeguards and website workflow | Submission requirements understood |
| 19:00 | Team plan review and mentor office hours | Saturday priorities locked |
| 20:30 | Checkpoint published on website | Visible starting point |
| 21:00 | Participant close | No overnight program |

## Saturday, 19 September · build and iterate

| Time | Activity | Result |
| --- | --- | --- |
| 09:00 | Stand-up and technical readiness | Blockers surfaced |
| 09:20 | Focused build block | Core journey implemented |
| 11:45 | Checkpoint review | Evidence and next changes recorded |
| 12:00 | Lunch | On-site meal |
| 13:00 | Build, user testing and mentor rotations | Product iteration |
| 15:15 | Tea break | Short reset |
| 15:35 | Final Saturday build block | Demo path stabilized |
| 16:35 | Website checkpoint and Sunday briefing | Submission plan confirmed |
| 17:00 | Close | No Saturday dinner |

ONCHAIN TIME BUILDER SPRINT  /  VENUE IN-KIND PROPOSAL

03 / SPACE AND INFRASTRUCTURE

# What a builder-ready venue needs

The ideal venue supports laptop-based team work, stable connectivity and a smooth Sunday transition into two simultaneous demo tracks.

## Required facilities

- Capacity and layout. Safe capacity for up to 80 people; team tables for laptop work; a central presentation zone; mentor corners; and catering/water space.

- Internet. Stable connectivity for approximately 100 simultaneous devices, a venue technical contact and permission for organizer-provided backup connectivity.

- Power. Sufficient safe outlets for every team, with clear rules for tested extension boards and cable covers.

- Presentation. One central screen or projector with microphone support, plus a display or projector for each Sunday demo track.

- Sunday separation. Two rooms or acoustically separated zones so both 15-minute demo tracks can operate simultaneously.

- Operating environment. Air conditioning, restrooms, drinking-water access, suitable lighting and accessibility information.

- Safety and access. Security, cleaning, entry procedures, emergency contacts, capacity limits and weekend opening/closing responsibility.

## Preferred room plan

| Zone | Use | Key requirement |
| --- | --- | --- |
| Team floor | 11–12 team tables plus circulation | Power at every table and reliable Wi-Fi |
| Central zone | Welcome, briefings and Saturday checkpoints | Main display, microphone and visible clock |
| Demo track A | Six Sunday team demos | Display, sound control and 20–30 audience seats |
| Demo track B | Six Sunday team demos | Separate display and acoustic separation |
| Mentor corners | Small-group product and technical support | Two quieter conversation points |
| Service zone | Registration, food, water and supplies | Delivery access without blocking team work |

ONCHAIN TIME BUILDER SPRINT  /  VENUE IN-KIND PROPOSAL

04 / SUNDAY DEMOS

# Two parallel tracks are enough for the expected teams

With 11–12 teams and two hours available, two tracks preserve meaningful product and feedback time while allowing the venue to close before lunch.

## Sunday, 20 September · 08:30–11:30

| Time | Activity | Output |
| --- | --- | --- |
| 08:30 | Coffee, light breakfast and final fixes | Demo-ready project |
| 09:15 | Direct website submission deadline | Stable project page and QR code |
| 09:20 | Demo briefing and track assignment | Teams and audiences positioned |
| 09:25–10:55 | Six rounds across two parallel demo tracks | Capacity for 12 complete demos |
| 10:55 | Feedback capture and transition | Next changes recorded online |
| 11:05 | Subtrack continuation plan | Owners, dates and pathway confirmed |
| 11:20 | Partner acknowledgement, photo and close | Program closes before lunch |
| 11:30 | Participants depart | No Sunday lunch |

DEMO CAPACITY 2 tracks × 6 rounds = 12 team demos. Each 15-minute slot allows approximately 7 minutes for the product, 5 minutes for feedback and 3 minutes for transition.

- Two separated zones. Each track needs a display, power, clear sound and one anchor mentor or facilitator.

- Website-first evidence. Every demo begins from the submitted project page and QR code.

- No local ranking. The close recognizes progress and readiness; the external subtrack governs its own eligibility and prizes.

## Sunday venue reset

- Both demo displays, power and network connections tested before 08:30.

- Track signs and team order posted before the 09:20 briefing.

- No shared public-address audio between tracks during the six demo rounds.

- Participant areas cleared by 11:30; organizer pack-down completed by 12:00.

ONCHAIN TIME BUILDER SPRINT  /  VENUE IN-KIND PROPOSAL

05 / PARTNER VALUE

# A visible role in Da Nang's builder pipeline

The venue partner becomes the physical home of a program connecting online learning, local technical talent and a continuation pathway into the Solana ecosystem.

## Venue partner benefits

- Official recognition. Named as Official Venue Partner on the event website, registration pages and participant communication.

- On-site visibility. Logo placement at registration, the central presentation area and both Sunday demo tracks, subject to brand guidelines.

- Opening participation. A short welcome during Friday kickoff and acknowledgement during Sunday's close.

- Talent access. Direct engagement with approximately 70 builders and visibility into 11–12 emerging project teams.

- Content and media. Access to approved event photographs, project links and a concise post-event impact report.

- Community association. Visible support for practical technology education and product-building activity in Da Nang.

## Recognition to confirm

| Channel | Proposed recognition |
| --- | --- |
| Website | Official Venue Partner name, logo and link |
| Registration and email | Partner acknowledgement in participant communications |
| On site | Entrance, main stage and demo-track logo placement |
| Program moments | Friday welcome and Sunday closing acknowledgement |
| Post-event | Inclusion in approved photo recap and impact report |

ONCHAIN TIME BUILDER SPRINT  /  VENUE IN-KIND PROPOSAL

06 / DELIVERY AND CONFIRMATION

# A short site review turns the proposal into an operating plan

Danh leads event operations. Hieu manages the venue relationship and program coordination. The venue appoints one primary contact and one weekend technical contact.

## Participant safeguards

- Published code of conduct and named escalation contacts.

- No overnight venue operations or expectation of overnight building.

- Dietary and accessibility needs collected before final room and catering plans.

- Photo consent and project-visibility choices included in registration and submission.

- First-aid supplies, emergency contacts and clear evacuation information.

## Site confirmation checklist

- Legal venue name, address, primary contact and weekend technical contact.

- Maximum safe capacity and agreed team-table layout.

- Exact access, opening, closing and pack-down procedure for all three days.

- Measured internet capacity, network access method and backup permissions.

- Power distribution, extension-board rules and cable-management requirements.

- Included screens, projectors, microphones, furniture, security and cleaning.

- Location and acoustic separation of the two Sunday demo tracks.

- Emergency, accessibility, catering-delivery and photography requirements.

- Commercial value of the in-kind contribution and agreed public recognition.

## Next steps

- Confirm interest. Agree in principle as soon as possible to support the dates, capacity and operating hours; online materials open on 4 September.

- Complete a site check and room plan. Validate internet, power, layout, access, AV and demo separation, then sign off catering delivery, security, cleaning and event zones.

- Document the contribution. Record the included services and normal commercial value of the venue support.

- Exchange contacts and brand assets. Confirm public naming, logo use and escalation routes.